## Rollout Timeline
Citykart Desk — Build & Rollout Plan ¦ Document date: 14-Sep-2026 ¦ Go-live: 28-Sep-2026
Phase / Module | Status | Start | Target / End | Notes | 03-Aug-2026 | 10-Aug-2026 | 17-Aug-2026 | 24-Aug-2026 | 31-Aug-2026 | 07-Sep-2026 | 14-Sep-2026 | 21-Sep-2026 | 28-Sep-2026 | 05-Oct-2026 | 12-Oct-2026 | 19-Oct-2026 | 26-Oct-2026 | 02-Nov-2026 | 09-Nov-2026 | 16-Nov-2026 | 23-Nov-2026 | 30-Nov-2026 | 07-Dec-2026 | 14-Dec-2026
BUILD HISTORY — HOW CORE WAS BUILT
CORE / 01 Kickoff & Rebrand | Completed | 06-Aug-2026 | 08-Aug-2026 | Single-tenant conversion from the base platform — the foundation Citykart Desk is built on
CORE / 02 Core Platform Build | Completed | 08-Aug-2026 | 13-Aug-2026 | Ticket lifecycle, RBAC, Report Builder, Field SLA Matrix, Business Rules engine
CORE / 03 Form Templates & Service Catalog | Completed | 27-Aug-2026 | 27-Aug-2026 | Design a form once, tag it to any service — instead of rebuilding per department
CORE / 04 Approvals & Workflow Hardening | Completed | 01-Sep-2026 | 03-Sep-2026 | SLA pause on approval, ticket reopen flow, bulk import, one-service-per-category rule
CORE / 05 Full System Audit | Completed | 09-Sep-2026 | 09-Sep-2026 | Security & data-isolation review across every module, ahead of UAT
CORE / 06 Core Desk — UAT Round | Completed | 10-Sep-2026 | 10-Sep-2026 | Functional, security & UI/UX testing, plus remediation and re-test on every finding
MODULE / WA WhatsApp Bot — Build & Internal UAT | Completed | 10-Sep-2026 | 11-Sep-2026 | Conversational ticket logging over WhatsApp — built end-to-end, internally tested
CORE / 07 OEM Routing, Notifications & Final Fixes | Completed | 14-Sep-2026 | 14-Sep-2026 | Store→OEM auto-mail, notification rules, web push, full fix pass; environment reset fresh
MILESTONE CORE CITYKART DESK — GO-LIVE | Go-Live | 18-Sep-2026 | 28-Sep-2026 | Hard date. Code goes live 18-Sep; all departments logging real tickets by 28-Sep, ticket numbering restarts at 1
ALL MODULES — CURRENT STATUS
MOD 01 Requests — Core Ticketing | Completed | 06-Aug-2026 | 28-Sep-2026 | Ticket lifecycle, categories, dynamic forms, store/requester linkage — live 28-Sep
MOD 02 Services — Catalog & Form Templates | Completed | 27-Aug-2026 | 28-Sep-2026 | Service catalog, categories/sub-categories, reusable form templates — live 28-Sep
MOD 03 Approvals | Completed | 01-Sep-2026 | 28-Sep-2026 | Multi-step & ad-hoc approval workflows, SLA pause during approval — live 28-Sep
MOD 04 Business Rules & SLA Automation | Completed | 10-Aug-2026 | 28-Sep-2026 | Auto-assign, escalation, Field SLA Matrix, business-hours-aware deadlines — live 28-Sep
MOD 05 Analytics — Report Builder | Completed | 09-Aug-2026 | 28-Sep-2026 | Excel-style pivot & table reports across every entity, xlsx export — live 28-Sep
MOD 06 Integrations — Notifications, Email & OEM Mail | Completed | 14-Sep-2026 | 28-Sep-2026 | Per-event notification rules, web push, configurable sender email, OEM auto-routing — live 28-Sep
MOD 07 Admin & Org Structure | Completed | 06-Aug-2026 | 28-Sep-2026 | Users, teams, roles, departments/locations, master data, audit logs — live 28-Sep
MOD 08 Intake — Email Channel | Built · Pending Setup | 14-Sep-2026 | TBD | Ticket creation from inbound email — code complete, needs a real mailbox connected (external)
MOD 09 Intake — WhatsApp Bot | Built · Pending Setup | 10-Sep-2026 | TBD | Log a ticket by chatting on WhatsApp — built & internally UAT'd; external pilot needs a real Meta Business account + public hosting (both external)
MOD 10 Time Tracking — DeskTime | Disconnected | 08-Aug-2026 | 14-Sep-2026 | Built, then deliberately disconnected — unused integration, on hold with no active plan
MOD 11 Projects | Not Started | — | — | Cross-functional project tracking with milestones — begins after core go-live
MOD 12 Tasks | Not Started | — | — | Team & personal task tracking, independent of the ticket queue — begins after core go-live

## Legend
Completed
In Progress
Milestone / Go-Live
Planned (external prerequisite pending)
Not Started / Disconnected
Red-bordered week column = TODAY (14-Sep-2026)