## Summary
CK Desk - what is live, what is ready, what is next
As on 2026-10-23. Live server build 20261022-154801 (checked read-only). Local = the development PC.
Stage | Features | What it means
1. LIVE on main | 99 | Built, tested and working on the live server today. Everyone can use it.
2. READY to go live | 40 | Built and tested on the development PC. Not on the live server yet. Each can go live as one release; the order and what each needs first are on sheet "2 Ready to go live".
3. FUTURE enhancements | 22 | Not built yet. Ideas from our own review, the ManageEngine comparison and pending decisions. Feedback from users and management is added on sheet "Feedback to add".
Area | Live | Ready to go live
Sign-in and accounts | 8 | 1
Raising a request | 10 | 1
Handling requests | 18 | 2
Conversation and e-mail | 10 | 0
SLA | 6 | 0
Approvals | 7 | 0
Automation | 3 | 1
Equipment (AC, Genset) and OEM | 3 | 2
Master data | 3 | 3
Vendor portal | 0 | 13
Purchase orders | 0 | 5
Dashboards - interactive | 14 | 1
Ticket Calendar | 0 | 10
Reports | 6 | 0
Projects, tasks, knowledge | 4 | 0
Customer satisfaction | 2 | 0
Intake channels | 0 | 0
Administration, security and logs | 5 | 1
Built but switched off: e-mail intake with human review (it is a decision, see sheet 3).
WhatsApp and DeskTime are not part of this list (left out on purpose).

## 1 Live on main
1. LIVE on the main server
# | Area | Feature | What it does (simple words) | Used by | Live since
1 | Sign-in and accounts | Sign in with e-mail and password | Everyone logs in with their e-mail; no public sign-up. | Requester, Technician, Manager/Admin, Vendor | Before 20 Sep 2026 (core)
2 | Sign-in and accounts | Forgot password and invitation by e-mail | Reset a password or accept an invitation by e-mail (sent through the app mailbox). | Requester, Technician, Manager/Admin, Vendor | 21 Sep 2026
3 | Sign-in and accounts | Password rules | No shared default password; random one-time passwords or invitations; must change on first sign-in. | Requester, Technician, Manager/Admin, Vendor | 19 Oct 2026
4 | Sign-in and accounts | My Profile | See who you report to and your team; set which notifications you want. | Requester, Technician, Manager/Admin | Before 20 Sep 2026 (core)
5 | Sign-in and accounts | Roles | Requester, technician, manager, admin, platform owner, each with its own pages and rights. | Manager/Admin | Before 20 Sep 2026 (core)
6 | Sign-in and accounts | Permission matrix with owner switches | Four switches the owner controls; defaults keep today's behaviour. | Manager/Admin | 19 Oct 2026
7 | Sign-in and accounts | User administration | Invite or create users, bulk Excel import, change role, change sign-in e-mail, deactivate, reset password. | Manager/Admin | Before 20 Sep 2026 (core)
8 | Sign-in and accounts | Technician groups and many groups per technician | Create groups; one technician can belong to several. | Technician, Manager/Admin | 1 Oct 2026
9 | Raising a request | Create Request page | One page with three panels and personal shortcuts to raise a request quickly. | Requester, Technician | 24 Sep 2026
10 | Raising a request | Service catalogue | Services with categories and sub categories, tags and locations. | Requester, Manager/Admin | Before 20 Sep 2026 (core)
11 | Raising a request | Dynamic forms per service | Each service has its own form: field types, required fields, conditions. | Requester, Manager/Admin | Before 20 Sep 2026 (core)
12 | Raising a request | Form Templates and Field Library | Reusable forms and reusable field definitions. | Manager/Admin | Before 20 Sep 2026 (core)
13 | Raising a request | Number and text limits in the form builder | Smallest and largest number, whole numbers only, shortest and longest text. | Manager/Admin, Requester | 22 Oct 2026
14 | Raising a request | Fields limited to categories | A field (for example Qty) appears only for chosen categories. | Manager/Admin, Requester | 19 Oct 2026
15 | Raising a request | Attachments with preview | Add files, get a clear popup if a file is too big, preview without downloading. | Requester, Technician | 3 Oct 2026
16 | Raising a request | Ticket title from the Subject field | The ticket is named after the Subject the requester typed. | Requester | 21 Sep 2026
17 | Raising a request | No double tickets | Pressing Submit twice within 15 seconds makes one ticket. | Requester | 19 Oct 2026
18 | Raising a request | Ticket numbers | Every request gets a number such as CKSD-000385. | Requester, Technician, Manager/Admin, Vendor | Before 20 Sep 2026 (core)
19 | Handling requests | Agent Requests (my queue and team queue) | Work queue with search by requester, store, technician, service and description; resolved hidden by default. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
20 | Handling requests | Assignment | Assign by hand, by Business Rules, round-robin or load-balanced. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
21 | Handling requests | Start working with first response | One click starts work and posts an automatic first response. | Technician | 5 Oct 2026
22 | Handling requests | Status flow with compulsory remarks | Open, In Progress, Waiting on user, Hold due to Purchase from HO, Resolved, Closed, Cancelled; remarks required. | Technician | Before 20 Sep 2026 (core)
23 | Handling requests | Hold due to Purchase from HO | A status for tickets waiting for a Head Office purchase; the clock pauses. | Technician | 30 Sep 2026
24 | Handling requests | Resolution note rules | A resolution note must say what was done (10+ characters) and never carry a password. | Technician | 15 Oct 2026
25 | Handling requests | Cancel with a remark | Requester or technician cancels; a remark is compulsory. | Requester, Technician | 22 Sep 2026
26 | Handling requests | Reopen a resolved request | Banner with a countdown, compulsory remark, expiry message. | Requester, Technician | 22 Sep 2026
27 | Handling requests | Reopen after a rejected approval | The requester can reopen within 48 hours. | Requester | 22 Sep 2026
28 | Handling requests | Priority from the sub category | Priority comes from the sub category; nobody can change it by hand. | Technician, Manager/Admin | 15 Oct 2026
29 | Handling requests | Service of a ticket is locked | Nobody can change the service of an existing ticket. | Manager/Admin | 15 Oct 2026
30 | Handling requests | Collaborators and related requests | Add people to a ticket; see related requests. | Technician | Before 20 Sep 2026 (core)
31 | Handling requests | "Catch me up" summary | A short summary of what happened and what is pending on a ticket. | Technician, Manager/Admin | 15 Oct 2026
32 | Handling requests | Ticket as PDF | Download the ticket, the form, the whole conversation and the history in one PDF. | Requester, Technician, Manager/Admin | 9 Oct 2026
33 | Handling requests | Automatic time tracking | Time starts when work starts and stops when it leaves In Progress. | Technician | Before 20 Sep 2026 (core)
34 | Handling requests | Nudge | Remind the handling technician from the dashboard. | Manager/Admin, Technician | Before 20 Sep 2026 (core)
35 | Handling requests | Bulk actions | Act on many tickets at once (up to 500). | Technician, Manager/Admin | Before 20 Sep 2026 (core)
36 | Handling requests | Ticket history | Every change recorded and shown as a timeline. | Requester, Technician | Before 20 Sep 2026 (core)
37 | Conversation and e-mail | Public conversation | Messages between requester and technician with files under each message. | Requester, Technician, Vendor | Before 20 Sep 2026 (core)
38 | Conversation and e-mail | Internal notes | Notes only Citykart staff can see. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
39 | Conversation and e-mail | CC a comment | Send a comment, with the whole ticket, to CK Desk users and OEM contacts. | Technician | 9 Oct 2026
40 | Conversation and e-mail | Reply by e-mail | A reply to a ticket mail is read from the mailbox every minute and added to the conversation. | Requester, Technician | 22 Sep 2026
41 | Conversation and e-mail | OEM e-mail on AC and Genset tickets | A table-style mail goes to the store's OEM automatically; OEM replies show in the conversation. | Technician | 3 Oct 2026
42 | Conversation and e-mail | Ticket e-mails | Mails for logged, assigned, status change, resolved, cancelled, with the technician's comment and real ticket title. | Requester, Technician | 21 Sep 2026
43 | Conversation and e-mail | Notification rules | Admin chooses, per event, in-app, e-mail or push; users can opt out. | Manager/Admin, Requester, Technician | 14 Sep 2026
44 | Conversation and e-mail | Bell, unread count and pop-up | A bell and a small corner pop-up for new notifications. | Requester, Technician, Manager/Admin, Vendor | 9 Oct 2026
45 | Conversation and e-mail | Browser push notifications | Optional push messages in the browser (asks once). | Requester, Technician, Manager/Admin, Vendor | 14 Sep 2026
46 | Conversation and e-mail | Mailbox settings | Admin sets the sending mailbox without a redeploy. | Manager/Admin | Before 20 Sep 2026 (core)
47 | SLA | SLA policies and business hours | Response and resolution targets per service and priority, business hours, holidays. | Manager/Admin | Before 20 Sep 2026 (core)
48 | SLA | Field-level SLA overrides | A form answer can set a shorter SLA. | Manager/Admin | Before 20 Sep 2026 (core)
49 | SLA | Pause and resume | The clock pauses while waiting on the user or on hold and resumes with the paused time credited. | Technician | Before 20 Sep 2026 (core)
50 | SLA | Breach views and highlights | "Currently breached", SLA compliance %, breach counts on dashboards and in reports. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
51 | SLA | Escalation and alert rules | Rules at 15-minute checks for SLA % used or unassigned tickets; alerts by e-mail. | Manager/Admin | Before 20 Sep 2026 (core)
52 | SLA | Daily alert digest | One summary mail every morning at 08:00. | Manager/Admin | Before 20 Sep 2026 (core)
53 | Approvals | Approval flows | Single or multi-step, sequential or parallel; flows set per service. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
54 | Approvals | Approve from the e-mail link | Approve or reject from a personal link with identity check and compulsory comment; links expire after 7 days. | Requester, Technician, Manager/Admin | 12 Oct 2026
55 | Approvals | Quick approve | Approve from the Approvals list or the bell. | Technician, Manager/Admin | 24 Sep 2026
56 | Approvals | Add approvers and delegate | Add approvers while pending; delegate a step; first answer decides. | Technician, Manager/Admin | 5 Oct 2026
57 | Approvals | Separation of duties | Nobody approves what they raised or sent. | Manager/Admin | 19 Oct 2026
58 | Approvals | Daily approval reminder | One mail at 10:00 to each approver listing what is waiting. | Manager/Admin | 15 Oct 2026
59 | Approvals | Automatic CVM approval | Fixtures / Hangers tickets go to the store's CVM for approval by themselves. | Technician, Requester | 19 Oct 2026
60 | Automation | Business Rules | No-code rules on create, update or schedule: assign, set status, priority, team, notify. | Manager/Admin | Before 20 Sep 2026 (core)
61 | Automation | Round-robin and load-balanced assignment | Spread tickets over technicians. | Manager/Admin | Before 20 Sep 2026 (core)
62 | Automation | Rule search | Find a rule by typing part of its name or description. | Manager/Admin | 14 Oct 2026
63 | Equipment (AC, Genset) and OEM | OEMs by type (AC and Genset) | One OEM per type per store; a category can send its tickets to the store's OEM. | Manager/Admin | 19 Oct 2026
64 | Equipment (AC, Genset) and OEM | Red-flag stores | Stores whose open AC tickets exceed a percentage of their ACs. | Technician, Manager/Admin | 12 Oct 2026
65 | Equipment (AC, Genset) and OEM | AC and AMC reports | Store AC Not Working, AMC vendor, AC issues, repeated AC complaints. | Technician, Manager/Admin | 12 Oct 2026
66 | Master data | Store Master | Stores with cluster, region, state, AC brand, priority list; Excel upload (with sample) and export. | Manager/Admin | 12 Oct 2026
67 | Master data | Organisation structure | Departments, locations, cost centres, job functions, designations. | Manager/Admin | Before 20 Sep 2026 (core)
68 | Master data | Store CVM | One CVM per store; one CVM can have many stores. | Manager/Admin | 19 Oct 2026
69 | Dashboards - interactive | Home dashboard | Counts and lists for you: my open, my queue, team open, my requests. | Requester, Technician, Manager/Admin | Before 20 Sep 2026 (core)
70 | Dashboards - interactive | Interactive Smart Dashboard | One dashboard for every role, narrowed to what the viewer may see; every number, bar and name can be clicked. | Requester, Technician, Manager/Admin | 8 Oct 2026
71 | Dashboards - interactive | KPI scorecard with trend | Created, resolved, backlog, breaches, SLA %, resolution time, CSAT, reopened, first response, each with a trend and the previous period. | Technician, Manager/Admin | 8 Oct 2026
72 | Dashboards - interactive | Click-to-drill pop-up (4 steps) | Click a number: cohort, then stores and technicians, then the ticket list, then one ticket with its history. | Technician, Manager/Admin | 8 Oct 2026
73 | Dashboards - interactive | Cascading filter bar | Group, technician, region, state, cluster, store type, OEM brand, AC health, status, SLA, search; each list shows only what fits the others. | Technician, Manager/Admin | 8 Oct 2026
74 | Dashboards - interactive | Time periods | 30, 60, 90, 120 days, this financial year or custom dates, with a compare-to-previous switch. | Technician, Manager/Admin | 8 Oct 2026
75 | Dashboards - interactive | Priority highlights strip | Six signals such as SLA risk, workload, OEM, approvals, AC red flags, new stores. | Technician, Manager/Admin | 8 Oct 2026
76 | Dashboards - interactive | Stores and Regions view | Regions, states, clusters and stores side by side with AC position. | Manager/Admin | 12 Oct 2026
77 | Dashboards - interactive | Group and OEM matrix | Group by OEM brand matrices with clickable cells. | Manager/Admin | 8 Oct 2026
78 | Dashboards - interactive | Workload and Approvals view | Technician workload and approvals waiting, with Nudge. | Manager/Admin | 8 Oct 2026
79 | Dashboards - interactive | Heatmap and ticket explorer | A ticket list that follows every filter, with heatmap. | Technician, Manager/Admin | 8 Oct 2026
80 | Dashboards - interactive | Export from the dashboard | Download the filtered tickets as CSV. | Technician, Manager/Admin | 9 Oct 2026
81 | Dashboards - interactive | Technician dashboard and workload | Group workload, 9-bucket ageing, daily activity, highest-open banner. | Technician, Manager/Admin | 24 Sep 2026
82 | Dashboards - interactive | Drag-and-drop dashboard widgets | Reorder widgets on the normal dashboards. | Technician, Manager/Admin | 1 Oct 2026
83 | Reports | Report Builder | Build your own pivot or table report from requests, tasks, projects, milestones and approvals. | Technician, Manager/Admin | Before 20 Sep 2026 (core)
84 | Reports | Saved reports | Save a report and open it again. | Technician, Manager/Admin | 1 Oct 2026
85 | Reports | Report Analytics | Fixed reports: age bucket, ticket status, store-wise, AC Not Working, AMC vendor (Excel-style, expand and collapse). | Technician, Manager/Admin | 8 Oct 2026
86 | Reports | Predefined Reports | 12 fixed Excel-style reports plus weekly, monthly, priority-wise and repeated AC complaint reports; search by name. | Technician, Manager/Admin | 12 Oct 2026
87 | Reports | Scheduled reports and exports | CSV and Excel exports; scheduled daily, weekly or monthly reports to company addresses. | Manager/Admin | Before 20 Sep 2026 (core)
88 | Reports | India-time reporting | Dates and weeks use India time everywhere. | Technician, Manager/Admin | 14 Oct 2026
89 | Projects, tasks, knowledge | Projects and milestones | Projects with owner, team, dates, milestones, updates and progress %. | Technician, Manager/Admin, Requester | Before 20 Sep 2026 (core)
90 | Projects, tasks, knowledge | Tasks | Personal and team tasks with subtasks, dependencies, templates, custom fields, comments, files. | Technician, Manager/Admin, Requester | Before 20 Sep 2026 (core)
91 | Projects, tasks, knowledge | Knowledge Base | Help articles per service. | Requester, Technician, Manager/Admin | Before 20 Sep 2026 (core)
92 | Projects, tasks, knowledge | Runbooks | A documentation browser for the admin set-up. | Manager/Admin | Before 20 Sep 2026 (core)
93 | Customer satisfaction | Rate the fix (CSAT) | One-click 1-5 stars in the "resolved" mail, or "not fixed, reopen"; one reminder. | Requester | 8 Oct 2026
94 | Customer satisfaction | Low-rating alert | An alert when a rating is low. | Manager/Admin | Before 20 Sep 2026 (core)
95 | Administration, security and logs | Categories, services and SLA set-up screens | All admin screens to define categories, services, templates, SLA, priorities, business hours. | Manager/Admin | Before 20 Sep 2026 (core)
96 | Administration, security and logs | Platform settings | Retention, integrations, sending mailbox. | Manager/Admin | Before 20 Sep 2026 (core)
97 | Administration, security and logs | Security hardening | Server-only writes, row-level security, per-purpose secrets, rate limits, report-only content policy, Next.js 16.3.8. | Manager/Admin | 13 - 19 Oct 2026
98 | Administration, security and logs | System Log (tamper-evident) | One Logs menu: system log with a hash chain, ticket activity, event log, errors, retention. | Manager/Admin | 14 Oct 2026
99 | Administration, security and logs | Monitoring and health | Live stats, health address, version address, log shipper. | Manager/Admin | 14 Oct 2026

## 2 Ready to go live
2. BUILT and READY to go live (not on the live server yet)
Release | Area | Feature | What it does (simple words) | Used by | Needs first
R1 | Raising a request | Pick your own AC | For an AC problem the form lists the store's own ACs from the AC sheet. | Requester | Nothing
R1 | Equipment (AC, Genset) and OEM | OEM mail again on reopen | When a store reopens a resolved ticket the OEM is mailed again. | Technician | Nothing
R1 | Master data | Google Sheets as master data | AC, Genset and CVM sheets copied into CK Desk at 11:00, 15:00, 19:00 or by "Update now". | Manager/Admin | Nothing
R1 | Master data | Sheet health page | Shows bad rows, bad addresses, approvers who are not CK Desk users. | Manager/Admin | Nothing
R3 | Master data | CVM from the sheet | The store's CVM comes from the CVM sheet. | Manager/Admin | R1
R5 | Equipment (AC, Genset) and OEM | AC and Genset master screens | Lists with filters, counts by brand, tonnage and region, Excel download. | Manager/Admin | R1
R8 | Sign-in and accounts | Vendor logins (technician and manager) | OEM engineers and their managers get their own limited logins. | Manager/Admin, Vendor | R1
R8 | Handling requests | Hand AC tickets to a vendor technician | Rules give the AC ticket to the OEM's engineer; the ticket shows "With vendor". | Manager/Admin, Technician | R1
R8 | Handling requests | End a vendor hold yourself | A Citykart technician can take the ticket back from hold; the vendor is told. | Technician | R1
R8 | Automation | Rules for vendor technicians | A rule can give a ticket to a vendor technician and never takes it away from him. | Manager/Admin | R1
R8 | Vendor portal | Vendor dashboard | Boxes: Revise price required, Open, In process, Part required, PO required, Resolved, Cancelled, each with whose turn it is. | Vendor | R1
R8 | Vendor portal | Vendor manager view | A vendor manager sees all tickets of his company, view only. | Vendor | R1
R8 | Vendor portal | Start working with the OEM ticket number | The engineer enters the OEM's ticket number to start; the store is told. | Vendor | R1
R8 | Vendor portal | Resolve with AC RESOLUTION list and FSR | Pick the fix from the list (or Other with a note) and attach the FSR (compulsory). | Vendor | R1
R8 | Vendor portal | Messages with the store | Two-way conversation with files. | Vendor, Requester | R1
R8 | Vendor portal | Safe vendor access | A vendor sees only his own tickets, cannot raise requests, never sees internal notes. | Vendor | R1
R9 | Vendor portal | Part required (no PO) | Parts list, ticket on hold, correct the list, withdraw, "Parts received" with a remark. | Vendor, Requester | R8
R10 | Vendor portal | PO required with a quote | Items with prices (without GST) and a compulsory quote file; approver told. | Vendor | R1, R8, R9
R10 | Vendor portal | Revise price required | The approver asks for a lower price; the ticket moves to a box; send a new quote. | Vendor | R1, R8, R9
R10 | Vendor portal | Quote versions | Every change is a new version; old versions cannot be approved. | Vendor, Manager/Admin | R1, R8, R9
R10 | Vendor portal | Reject only the quote | The ticket goes on; the vendor arranges the parts himself. | Vendor, Manager/Admin | R1, R8, R9
R10 | Purchase orders | PO approval page | Approve (PO number, date, document), ask for a revised price, reject quote only, or reject and cancel. | Manager/Admin | R1, R8, R9
R10 | Purchase orders | Approvers from the AC sheet | The AC sheet names the approvers per AC (several allowed); one mail to all; first decision wins. | Manager/Admin | R1, R8, R9
R10 | Purchase orders | Default PO approver | Used when the sheet names nobody. | Manager/Admin | R1, R8, R9
R10 | Purchase orders | Purchase orders register | All POs with search and Excel download; vendors see their own. | Manager/Admin, Vendor | R1, R8, R9
R10 | Purchase orders | OEM mail on PO decision | The OEM gets the approved PO with the document, or a short rejection note. | Manager/Admin | R1, R8, R9
R11 | Vendor portal | Vendor e-mails | Mails for assigned, revised price, PO approved (with document), quote not approved, cancelled, reopened, hold ended. | Vendor | R8 to R10 (ships with them)
R11 | Vendor portal | Reopened tag | A red "Reopened xN" tag and the old OEM ticket number cleared. | Vendor | R8 to R10 (ships with them)
R12 | Dashboards - interactive | Service, Category and Sub category filters | Three more filters in the dashboard bar, each narrowing the next. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Ticket Calendar for every group | A month calendar named after the group ("IT Ticket Calendar"); days coloured green, yellow, red, grey for the future. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Colour by the group's own normal | For groups without assets the colour compares each day with that group's usual open level over 90 days. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Place picker | Look at all Citykart, a state, region, cluster or one store. | Technician, Manager/Admin, Requester | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Faulty AC and genset calendar | For AC and Genset work: share of faulty machines per day (above 10% yellow, above 30% red), raised and fixed. | Technician, Manager/Admin, Requester | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | ACs that fail again and again | Repeat-fault ACs by serial number (4+ = repeat, 2-3 = watch) with "came back within 30 days of a fix" and who fixed it last. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Same issue again | Same store and same issue raised again; the repeat list for groups without assets. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Break it down by | Technician, cluster, region, state, store, category, sub category: open now, raised, fixed. | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Day pop-up | Click a day to see the tickets raised, fixed and still open that day. | Technician, Manager/Admin, Requester | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Worst places right now | Ranking of stores, clusters, regions or states by share of faulty ACs; click to open. | Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Ticket Calendar | Outside temperature | Highest and lowest temperature per day for the place, collected once a day at 08:00 (AC and genset views only). | Technician, Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
R12 | Administration, security and logs | Daily weather job | A scheduled task at 08:00 that saves the day's highest and lowest temperature of each city. | Manager/Admin | The ticket-count view needs nothing; the AC and genset view needs R1 (and R2)
Release | What the release is |  | What it contains | Database step on the server | Risk
R1 | AC Google Sheet is the master |  | The AC sheet is copied into CK Desk three times a day; the ticket form shows the store's own ACs; the OEM mail comes from the sheet. Your steps: Connect Google (needs a one-time localhost step), give the sheet address, add one scheduled task. Needs first: Nothing. | Yes (new tables only) | Medium
R2 | Genset Google Sheet |  | Same idea for gensets: one mail to every OEM address of the store's gensets. Your steps: Switch on in Admin. Needs first: R1. | Yes | Low-Medium
R3 | CVM Google Sheet |  | The store's CVM comes from the CVM sheet. Your steps: Switch on in Admin. Needs first: R1. | Yes | Medium
R5 | AC and Genset master screens |  | Lists with filters, counts and Excel download. Your steps: Nothing. Needs first: R1. | No | Low
R8 | Vendor technicians - core |  | OEM engineers log in and work their AC tickets; vendor manager sees the company, view only. Your steps: Create vendor companies and logins; write the routing rules (they must run before the old "Krishan" rule). Needs first: R1. | Yes | Medium-High
R9 | Vendor - Part required |  | Parts list, ticket on hold, Parts received. Your steps: Nothing. Needs first: R8. | Yes | Medium
R10 | Vendor - PO required |  | Quote with file, approval, revised price, quote versions, PO register; approvers from the AC sheet. Your steps: Add the three AC sheet columns (OEM Ticket Mail To, OEM PO Mail To, CK PO Approver Mail To); set the default approver. Needs first: R1, R8, R9. | Yes | Medium-High
R11 | Vendor mails and the Reopened tag |  | All the vendor, store and OEM mails of the vendor flow. Your steps: Nothing. Needs first: R8 to R10 (ships with them). | No | Low
R12 | Ticket Calendar and the new filters |  | Calendar for every group; Service, Category and Sub category filters; daily outside temperature. Your steps: Add one scheduled task at 08:00 (the server can already reach the weather service). Needs first: The ticket-count view needs nothing; the AC and genset view needs R1 (and R2). | Yes (weather tables) | Medium
Suggested order: R1, then R5, then R2 and R3 after a few calm days, then the vendor set R8, R9, R10 (+R11), and R12 (the ticket-count calendar can go earlier). Each is pushed only when you say so, one at a time.

## 3 Future enhancements
3. FUTURE enhancements (not built yet)
# | Enhancement | What it would do (simple words) | Why it helps | Where the idea came from | Priority | Status
1 | Reminder for a waiting quote | Mail the approver after 1 day if a quote is waiting, and the vendor after 2 days if a revised price is not answered. | Stops quotes getting stuck. | Our list |  | Not started
2 | Vendor replies by e-mail | A vendor answers a ticket mail and the reply appears in the conversation (to be tested for vendors). | Easier for engineers in the field. | Our list |  | Not started
3 | More dashboard figures from the sheets | ACs by brand, region and AMC vendor; repeat-failure ACs on the main dashboard. | Management view of equipment health. | Our list |  | Not started
4 | Calendar: correct reopened tickets | Use the ticket history so a reopened ticket is counted only for the time it was really open. | More accurate calendar colours. | Our list |  | Not started
5 | Calendar: year view and weekday pattern | Twelve small months side by side; which weekdays are busiest. | Shows the summer peak at a glance. | Our list |  | Not started
6 | Weather fallback by nearest store | For cities the weather service cannot find, use the nearest store of the same cluster. | Every store gets a temperature. | Our list |  | Not started
7 | Fix city names in the Store Master | Correct about 20 misspelt or wrong-state city names so each store has a temperature. | Data quality. | Our list |  | Not started
8 | Preventive maintenance | Create AC servicing tickets automatically every month or quarter. | Fewer breakdowns; ManageEngine has this. | ManageEngine comparison |  | Not started
9 | Problem management for repeat faults | Open a "problem" for an AC that keeps failing and track the root cause and the replacement decision. | Turns the repeat list into action. | ManageEngine comparison |  | Not started
10 | Asset register beyond AC and Genset | A list of other equipment (fans, fixtures, water coolers) with history. | One view of all equipment. | ManageEngine comparison |  | Not started
11 | Mobile app | An installable app for technicians and stores (today: the website works on phones, with browser push). | Field staff convenience. | ManageEngine comparison |  | Not started
12 | Technician shifts and on-call | Who is available and who is on call. | Better assignment. | ManageEngine comparison |  | Not started
13 | Several escalation levels | More than one escalation step when an SLA is at risk. | Faster response to risk. | ManageEngine comparison |  | Not started
14 | Merge duplicate tickets | Combine two tickets about the same problem. | Cleaner queues. | ManageEngine comparison |  | Not started
15 | CK Desk Bot | Ask questions in plain words about tickets and the knowledge base. | Quicker answers. | Our list (plan only) |  | Not started
16 | Google Workspace user sync | Create and update users from Google Workspace. | Less admin work. | Our list (plan only) |  | Not started
17 | Switch on e-mail intake | Turn on the already-built e-mail intake with human review (decision needed). | Tickets from mail. | Decision pending |  | Not started
18 | Secure web address (HTTPS) | A company web address with HTTPS; also removes the Google sign-in restriction. | Safer and simpler Google set-up. | Operations |  | Not started
19 | Remove the temporary security setting | Turn off the temporary shared-secret setting that is still on in the live system. | Security housekeeping. | Operations |  | Not started
20 | Make the permission matrix real | Today it is only a display; decide to wire it up or remove it. | Clear permissions. | Decision pending |  | Not started
21 | First-response clock after a reopen | Decide whether the response time restarts when a ticket is reopened (today only the resolution time restarts). | Fair SLA reporting. | Decision pending |  | Not started
22 | Remaining small security items | The few low-risk findings left in the audit register. | Security housekeeping. | Operations |  | Not started

## Feedback to add
Feedback from users and management - paste your feedback rows here
ID | Date | Raised by | Feedback / request (as received) | Proposed feature | Priority | Status | Target release
F-001 | [5 empty] | New
F-002 | [5 empty] | New
F-003 | [5 empty] | New
F-004 | [5 empty] | New
F-005 | [5 empty] | New
F-006 | [5 empty] | New
F-007 | [5 empty] | New
F-008 | [5 empty] | New
F-009 | [5 empty] | New
F-010 | [5 empty] | New
F-011 | [5 empty] | New
F-012 | [5 empty] | New

## All features (detail)
Feature name | What it does | Local dev server | Main (live) server | Area | Used by | Nearest area in ManageEngine ServiceDesk Plus | Release
Sign in with e-mail and password | Everyone logs in with their e-mail; no public sign-up. | Done | Done | Sign-in and accounts | Requester, Technician, Manager/Admin, Vendor | Self-service portal login
Forgot password and invitation by e-mail | Reset a password or accept an invitation by e-mail (sent through the app mailbox). | Done | Done | Sign-in and accounts | Requester, Technician, Manager/Admin, Vendor | Self-service portal login
Password rules | No shared default password; random one-time passwords or invitations; must change on first sign-in. | Done | Done | Sign-in and accounts | Requester, Technician, Manager/Admin, Vendor | Security settings
My Profile | See who you report to and your team; set which notifications you want. | Done | Done | Sign-in and accounts | Requester, Technician, Manager/Admin | My profile
Roles | Requester, technician, manager, admin, platform owner, each with its own pages and rights. | Done | Done | Sign-in and accounts | Manager/Admin | Roles and permissions
Permission matrix with owner switches | Four switches the owner controls; defaults keep today's behaviour. | Done | Done | Sign-in and accounts | Manager/Admin | Roles and permissions
User administration | Invite or create users, bulk Excel import, change role, change sign-in e-mail, deactivate, reset password. | Done | Done | Sign-in and accounts | Manager/Admin | Users
Technician groups and many groups per technician | Create groups; one technician can belong to several. | Done | Done | Sign-in and accounts | Technician, Manager/Admin | Technician groups
Vendor logins (technician and manager) | OEM engineers and their managers get their own limited logins. | Done | Pending | Sign-in and accounts | Manager/Admin, Vendor | Vendor portal (no direct equivalent) | R8
Create Request page | One page with three panels and personal shortcuts to raise a request quickly. | Done | Done | Raising a request | Requester, Technician | New request / self-service portal
Service catalogue | Services with categories and sub categories, tags and locations. | Done | Done | Raising a request | Requester, Manager/Admin | Service catalog
Dynamic forms per service | Each service has its own form: field types, required fields, conditions. | Done | Done | Raising a request | Requester, Manager/Admin | Request templates
Form Templates and Field Library | Reusable forms and reusable field definitions. | Done | Done | Raising a request | Manager/Admin | Request templates / custom fields
Number and text limits in the form builder | Smallest and largest number, whole numbers only, shortest and longest text. | Done | Done | Raising a request | Manager/Admin, Requester | Field validation
Fields limited to categories | A field (for example Qty) appears only for chosen categories. | Done | Done | Raising a request | Manager/Admin, Requester | Conditional fields
Attachments with preview | Add files, get a clear popup if a file is too big, preview without downloading. | Done | Done | Raising a request | Requester, Technician | Attachments
Ticket title from the Subject field | The ticket is named after the Subject the requester typed. | Done | Done | Raising a request | Requester | Request subject
No double tickets | Pressing Submit twice within 15 seconds makes one ticket. | Done | Done | Raising a request | Requester | Duplicate prevention
Ticket numbers | Every request gets a number such as CKSD-000385. | Done | Done | Raising a request | Requester, Technician, Manager/Admin, Vendor | Request ID
Pick your own AC | For an AC problem the form lists the store's own ACs from the AC sheet. | Done | Pending | Raising a request | Requester | Asset selection on request | R1
Agent Requests (my queue and team queue) | Work queue with search by requester, store, technician, service and description; resolved hidden by default. | Done | Done | Handling requests | Technician, Manager/Admin | Request list and views
Assignment | Assign by hand, by Business Rules, round-robin or load-balanced. | Done | Done | Handling requests | Technician, Manager/Admin | Assign / auto-assign
Start working with first response | One click starts work and posts an automatic first response. | Done | Done | Handling requests | Technician | First response
Status flow with compulsory remarks | Open, In Progress, Waiting on user, Hold due to Purchase from HO, Resolved, Closed, Cancelled; remarks required. | Done | Done | Handling requests | Technician | Request status
Hold due to Purchase from HO | A status for tickets waiting for a Head Office purchase; the clock pauses. | Done | Done | Handling requests | Technician | On hold status
Resolution note rules | A resolution note must say what was done (10+ characters) and never carry a password. | Done | Done | Handling requests | Technician | Closure rules
Cancel with a remark | Requester or technician cancels; a remark is compulsory. | Done | Done | Handling requests | Requester, Technician | Close / cancel request
Reopen a resolved request | Banner with a countdown, compulsory remark, expiry message. | Done | Done | Handling requests | Requester, Technician | Reopen request
Reopen after a rejected approval | The requester can reopen within 48 hours. | Done | Done | Handling requests | Requester | Reopen request
Priority from the sub category | Priority comes from the sub category; nobody can change it by hand. | Done | Done | Handling requests | Technician, Manager/Admin | Priority matrix
Service of a ticket is locked | Nobody can change the service of an existing ticket. | Done | Done | Handling requests | Manager/Admin | Request lock
Collaborators and related requests | Add people to a ticket; see related requests. | Done | Done | Handling requests | Technician | Collaborators / linked requests
"Catch me up" summary | A short summary of what happened and what is pending on a ticket. | Done | Done | Handling requests | Technician, Manager/Admin | No direct equivalent (AI summary in ME's AI add-on)
Ticket as PDF | Download the ticket, the form, the whole conversation and the history in one PDF. | Done | Done | Handling requests | Requester, Technician, Manager/Admin | Print / export request
Automatic time tracking | Time starts when work starts and stops when it leaves In Progress. | Done | Done | Handling requests | Technician | Worklogs and timers
Nudge | Remind the handling technician from the dashboard. | Done | Done | Handling requests | Manager/Admin, Technician | Reminders / escalation
Bulk actions | Act on many tickets at once (up to 500). | Done | Done | Handling requests | Technician, Manager/Admin | Bulk actions
Ticket history | Every change recorded and shown as a timeline. | Done | Done | Handling requests | Requester, Technician | Request history
Hand AC tickets to a vendor technician | Rules give the AC ticket to the OEM's engineer; the ticket shows "With vendor". | Done | Pending | Handling requests | Manager/Admin, Technician | No direct equivalent | R8
End a vendor hold yourself | A Citykart technician can take the ticket back from hold; the vendor is told. | Done | Pending | Handling requests | Technician | No direct equivalent | R8
Public conversation | Messages between requester and technician with files under each message. | Done | Done | Conversation and e-mail | Requester, Technician, Vendor | Conversation / replies
Internal notes | Notes only Citykart staff can see. | Done | Done | Conversation and e-mail | Technician, Manager/Admin | Notes
CC a comment | Send a comment, with the whole ticket, to CK Desk users and OEM contacts. | Done | Done | Conversation and e-mail | Technician | Forward / CC on reply
Reply by e-mail | A reply to a ticket mail is read from the mailbox every minute and added to the conversation. | Done | Done | Conversation and e-mail | Requester, Technician | E-mail reply to request
OEM e-mail on AC and Genset tickets | A table-style mail goes to the store's OEM automatically; OEM replies show in the conversation. | Done | Done | Conversation and e-mail | Technician | Notify vendor
Ticket e-mails | Mails for logged, assigned, status change, resolved, cancelled, with the technician's comment and real ticket title. | Done | Done | Conversation and e-mail | Requester, Technician | Notification templates
Notification rules | Admin chooses, per event, in-app, e-mail or push; users can opt out. | Done | Done | Conversation and e-mail | Manager/Admin, Requester, Technician | Notification rules
Bell, unread count and pop-up | A bell and a small corner pop-up for new notifications. | Done | Done | Conversation and e-mail | Requester, Technician, Manager/Admin, Vendor | Notifications
Browser push notifications | Optional push messages in the browser (asks once). | Done | Done | Conversation and e-mail | Requester, Technician, Manager/Admin, Vendor | Mobile / push notifications
Mailbox settings | Admin sets the sending mailbox without a redeploy. | Done | Done | Conversation and e-mail | Manager/Admin | Mail server settings
SLA policies and business hours | Response and resolution targets per service and priority, business hours, holidays. | Done | Done | SLA | Manager/Admin | SLAs
Field-level SLA overrides | A form answer can set a shorter SLA. | Done | Done | SLA | Manager/Admin | SLA rules
Pause and resume | The clock pauses while waiting on the user or on hold and resumes with the paused time credited. | Done | Done | SLA | Technician | SLA hold
Breach views and highlights | "Currently breached", SLA compliance %, breach counts on dashboards and in reports. | Done | Done | SLA | Technician, Manager/Admin | SLA reports
Escalation and alert rules | Rules at 15-minute checks for SLA % used or unassigned tickets; alerts by e-mail. | Done | Done | SLA | Manager/Admin | Escalations
Daily alert digest | One summary mail every morning at 08:00. | Done | Done | SLA | Manager/Admin | Scheduled reports
Approval flows | Single or multi-step, sequential or parallel; flows set per service. | Done | Done | Approvals | Technician, Manager/Admin | Approvals
Approve from the e-mail link | Approve or reject from a personal link with identity check and compulsory comment; links expire after 7 days. | Done | Done | Approvals | Requester, Technician, Manager/Admin | Approve by e-mail
Quick approve | Approve from the Approvals list or the bell. | Done | Done | Approvals | Technician, Manager/Admin | Approvals
Add approvers and delegate | Add approvers while pending; delegate a step; first answer decides. | Done | Done | Approvals | Technician, Manager/Admin | Approvals
Separation of duties | Nobody approves what they raised or sent. | Done | Done | Approvals | Manager/Admin | Approval rules
Daily approval reminder | One mail at 10:00 to each approver listing what is waiting. | Done | Done | Approvals | Manager/Admin | Approval reminders
Automatic CVM approval | Fixtures / Hangers tickets go to the store's CVM for approval by themselves. | Done | Done | Approvals | Technician, Requester | No direct equivalent
Business Rules | No-code rules on create, update or schedule: assign, set status, priority, team, notify. | Done | Done | Automation | Manager/Admin | Business rules
Round-robin and load-balanced assignment | Spread tickets over technicians. | Done | Done | Automation | Manager/Admin | Auto-assign
Rule search | Find a rule by typing part of its name or description. | Done | Done | Automation | Manager/Admin | Business rules
Rules for vendor technicians | A rule can give a ticket to a vendor technician and never takes it away from him. | Done | Pending | Automation | Manager/Admin | No direct equivalent | R8
OEMs by type (AC and Genset) | One OEM per type per store; a category can send its tickets to the store's OEM. | Done | Done | Equipment (AC, Genset) and OEM | Manager/Admin | Vendors
Red-flag stores | Stores whose open AC tickets exceed a percentage of their ACs. | Done | Done | Equipment (AC, Genset) and OEM | Technician, Manager/Admin | Reports
AC and AMC reports | Store AC Not Working, AMC vendor, AC issues, repeated AC complaints. | Done | Done | Equipment (AC, Genset) and OEM | Technician, Manager/Admin | Asset reports
OEM mail again on reopen | When a store reopens a resolved ticket the OEM is mailed again. | Done | Pending | Equipment (AC, Genset) and OEM | Technician | Notify vendor | R1
AC and Genset master screens | Lists with filters, counts by brand, tonnage and region, Excel download. | Done | Pending | Equipment (AC, Genset) and OEM | Manager/Admin | Asset list | R5
Store Master | Stores with cluster, region, state, AC brand, priority list; Excel upload (with sample) and export. | Done | Done | Master data | Manager/Admin | Sites / locations
Organisation structure | Departments, locations, cost centres, job functions, designations. | Done | Done | Master data | Manager/Admin | Departments / sites
Store CVM | One CVM per store; one CVM can have many stores. | Done | Done | Master data | Manager/Admin | No direct equivalent
Google Sheets as master data | AC, Genset and CVM sheets copied into CK Desk at 11:00, 15:00, 19:00 or by "Update now". | Done | Pending | Master data | Manager/Admin | Asset import | R1
Sheet health page | Shows bad rows, bad addresses, approvers who are not CK Desk users. | Done | Pending | Master data | Manager/Admin | Import log | R1
CVM from the sheet | The store's CVM comes from the CVM sheet. | Done | Pending | Master data | Manager/Admin | No direct equivalent | R3
Vendor dashboard | Boxes: Revise price required, Open, In process, Part required, PO required, Resolved, Cancelled, each with whose turn it is. | Done | Pending | Vendor portal | Vendor | Technician portal | R8
Vendor manager view | A vendor manager sees all tickets of his company, view only. | Done | Pending | Vendor portal | Vendor | No direct equivalent | R8
Start working with the OEM ticket number | The engineer enters the OEM's ticket number to start; the store is told. | Done | Pending | Vendor portal | Vendor | No direct equivalent | R8
Resolve with AC RESOLUTION list and FSR | Pick the fix from the list (or Other with a note) and attach the FSR (compulsory). | Done | Pending | Vendor portal | Vendor | Resolution | R8
Messages with the store | Two-way conversation with files. | Done | Pending | Vendor portal | Vendor, Requester | Conversation | R8
Part required (no PO) | Parts list, ticket on hold, correct the list, withdraw, "Parts received" with a remark. | Done | Pending | Vendor portal | Vendor, Requester | Purchase request | R9
PO required with a quote | Items with prices (without GST) and a compulsory quote file; approver told. | Done | Pending | Vendor portal | Vendor | Purchase order request | R10
Revise price required | The approver asks for a lower price; the ticket moves to a box; send a new quote. | Done | Pending | Vendor portal | Vendor | Quote negotiation | R10
Quote versions | Every change is a new version; old versions cannot be approved. | Done | Pending | Vendor portal | Vendor, Manager/Admin | Purchase order versions | R10
Reject only the quote | The ticket goes on; the vendor arranges the parts himself. | Done | Pending | Vendor portal | Vendor, Manager/Admin | No direct equivalent | R10
Vendor e-mails | Mails for assigned, revised price, PO approved (with document), quote not approved, cancelled, reopened, hold ended. | Done | Pending | Vendor portal | Vendor | Notification templates | R11
Reopened tag | A red "Reopened xN" tag and the old OEM ticket number cleared. | Done | Pending | Vendor portal | Vendor | No direct equivalent | R11
Safe vendor access | A vendor sees only his own tickets, cannot raise requests, never sees internal notes. | Done | Pending | Vendor portal | Vendor | Roles | R8
PO approval page | Approve (PO number, date, document), ask for a revised price, reject quote only, or reject and cancel. | Done | Pending | Purchase orders | Manager/Admin | Purchase approval | R10
Approvers from the AC sheet | The AC sheet names the approvers per AC (several allowed); one mail to all; first decision wins. | Done | Pending | Purchase orders | Manager/Admin | Approval by site / group | R10
Default PO approver | Used when the sheet names nobody. | Done | Pending | Purchase orders | Manager/Admin | Approval settings | R10
Purchase orders register | All POs with search and Excel download; vendors see their own. | Done | Pending | Purchase orders | Manager/Admin, Vendor | Purchase orders list | R10
OEM mail on PO decision | The OEM gets the approved PO with the document, or a short rejection note. | Done | Pending | Purchase orders | Manager/Admin | Purchase order e-mail | R10
Home dashboard | Counts and lists for you: my open, my queue, team open, my requests. | Done | Done | Dashboards - interactive | Requester, Technician, Manager/Admin | Home / dashboard
Interactive Smart Dashboard | One dashboard for every role, narrowed to what the viewer may see; every number, bar and name can be clicked. | Done | Done | Dashboards - interactive | Requester, Technician, Manager/Admin | Dashboards and widgets
KPI scorecard with trend | Created, resolved, backlog, breaches, SLA %, resolution time, CSAT, reopened, first response, each with a trend and the previous period. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Dashboard widgets
Click-to-drill pop-up (4 steps) | Click a number: cohort, then stores and technicians, then the ticket list, then one ticket with its history. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Drill-down on widgets
Cascading filter bar | Group, technician, region, state, cluster, store type, OEM brand, AC health, status, SLA, search; each list shows only what fits the others. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Dashboard filters
Time periods | 30, 60, 90, 120 days, this financial year or custom dates, with a compare-to-previous switch. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Date range
Priority highlights strip | Six signals such as SLA risk, workload, OEM, approvals, AC red flags, new stores. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | No direct equivalent
Stores and Regions view | Regions, states, clusters and stores side by side with AC position. | Done | Done | Dashboards - interactive | Manager/Admin | No direct equivalent
Group and OEM matrix | Group by OEM brand matrices with clickable cells. | Done | Done | Dashboards - interactive | Manager/Admin | Pivot widgets
Workload and Approvals view | Technician workload and approvals waiting, with Nudge. | Done | Done | Dashboards - interactive | Manager/Admin | Technician workload
Heatmap and ticket explorer | A ticket list that follows every filter, with heatmap. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Request list
Export from the dashboard | Download the filtered tickets as CSV. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Export
Technician dashboard and workload | Group workload, 9-bucket ageing, daily activity, highest-open banner. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Technician dashboard
Drag-and-drop dashboard widgets | Reorder widgets on the normal dashboards. | Done | Done | Dashboards - interactive | Technician, Manager/Admin | Dashboard personalisation
Service, Category and Sub category filters | Three more filters in the dashboard bar, each narrowing the next. | Done | Pending | Dashboards - interactive | Technician, Manager/Admin | Dashboard filters | R12
Ticket Calendar for every group | A month calendar named after the group ("IT Ticket Calendar"); days coloured green, yellow, red, grey for the future. | Done | Pending | Ticket Calendar | Technician, Manager/Admin | No direct equivalent (ME has a calendar for tasks and changes only) | R12
Colour by the group's own normal | For groups without assets the colour compares each day with that group's usual open level over 90 days. | Done | Pending | Ticket Calendar | Technician, Manager/Admin | No direct equivalent | R12
Place picker | Look at all Citykart, a state, region, cluster or one store. | Done | Pending | Ticket Calendar | Technician, Manager/Admin, Requester | No direct equivalent | R12
Faulty AC and genset calendar | For AC and Genset work: share of faulty machines per day (above 10% yellow, above 30% red), raised and fixed. | Done | Pending | Ticket Calendar | Technician, Manager/Admin, Requester | Asset health (partial) | R12
ACs that fail again and again | Repeat-fault ACs by serial number (4+ = repeat, 2-3 = watch) with "came back within 30 days of a fix" and who fixed it last. | Done | Pending | Ticket Calendar | Technician, Manager/Admin | Asset history (partial) | R12
Same issue again | Same store and same issue raised again; the repeat list for groups without assets. | Done | Pending | Ticket Calendar | Technician, Manager/Admin | Problem management (partial) | R12
Break it down by | Technician, cluster, region, state, store, category, sub category: open now, raised, fixed. | Done | Pending | Ticket Calendar | Technician, Manager/Admin | Dashboard widgets | R12
Day pop-up | Click a day to see the tickets raised, fixed and still open that day. | Done | Pending | Ticket Calendar | Technician, Manager/Admin, Requester | Drill-down on widgets | R12
Worst places right now | Ranking of stores, clusters, regions or states by share of faulty ACs; click to open. | Done | Pending | Ticket Calendar | Manager/Admin | No direct equivalent | R12
Outside temperature | Highest and lowest temperature per day for the place, collected once a day at 08:00 (AC and genset views only). | Done | Pending | Ticket Calendar | Technician, Manager/Admin | No direct equivalent | R12
Report Builder | Build your own pivot or table report from requests, tasks, projects, milestones and approvals. | Done | Done | Reports | Technician, Manager/Admin | Report builder
Saved reports | Save a report and open it again. | Done | Done | Reports | Technician, Manager/Admin | Custom reports
Report Analytics | Fixed reports: age bucket, ticket status, store-wise, AC Not Working, AMC vendor (Excel-style, expand and collapse). | Done | Done | Reports | Technician, Manager/Admin | Standard reports
Predefined Reports | 12 fixed Excel-style reports plus weekly, monthly, priority-wise and repeated AC complaint reports; search by name. | Done | Done | Reports | Technician, Manager/Admin | Standard reports
Scheduled reports and exports | CSV and Excel exports; scheduled daily, weekly or monthly reports to company addresses. | Done | Done | Reports | Manager/Admin | Scheduled reports
India-time reporting | Dates and weeks use India time everywhere. | Done | Done | Reports | Technician, Manager/Admin | Time zone settings
Projects and milestones | Projects with owner, team, dates, milestones, updates and progress %. | Done | Done | Projects, tasks, knowledge | Technician, Manager/Admin, Requester | Projects
Tasks | Personal and team tasks with subtasks, dependencies, templates, custom fields, comments, files. | Done | Done | Projects, tasks, knowledge | Technician, Manager/Admin, Requester | Tasks
Knowledge Base | Help articles per service. | Done | Done | Projects, tasks, knowledge | Requester, Technician, Manager/Admin | Solutions
Runbooks | A documentation browser for the admin set-up. | Done | Done | Projects, tasks, knowledge | Manager/Admin | No direct equivalent
Rate the fix (CSAT) | One-click 1-5 stars in the "resolved" mail, or "not fixed, reopen"; one reminder. | Done | Done | Customer satisfaction | Requester | Surveys
Low-rating alert | An alert when a rating is low. | Done | Done | Customer satisfaction | Manager/Admin | Survey alerts
E-mail intake with human review | Mails are classified (rules, optional AI) and a reviewer turns them into tickets. | Done | Built - switched off | Intake channels | Manager/Admin | E-mail commands / mail fetching
Intake rules and classification | Rules and an optional AI model sort incoming messages. | Done | Built - switched off | Intake channels | Manager/Admin | Zia / AI add-on
Categories, services and SLA set-up screens | All admin screens to define categories, services, templates, SLA, priorities, business hours. | Done | Done | Administration, security and logs | Manager/Admin | Admin settings
Platform settings | Retention, integrations, sending mailbox. | Done | Done | Administration, security and logs | Manager/Admin | Admin settings
Security hardening | Server-only writes, row-level security, per-purpose secrets, rate limits, report-only content policy, Next.js 16.3.8. | Done | Done | Administration, security and logs | Manager/Admin | Security
System Log (tamper-evident) | One Logs menu: system log with a hash chain, ticket activity, event log, errors, retention. | Done | Done | Administration, security and logs | Manager/Admin | Audit / logs
Monitoring and health | Live stats, health address, version address, log shipper. | Done | Done | Administration, security and logs | Manager/Admin | Server monitoring
Daily weather job | A scheduled task at 08:00 that saves the day's highest and lowest temperature of each city. | Done | Pending | Administration, security and logs | Manager/Admin | No direct equivalent | R12
Reminder for a waiting quote | Remind the approver after 1 day and the vendor after 2 days. | Pending | Pending | Not built yet | Manager/Admin, Vendor | Escalations
Vendor replies by e-mail | A vendor answers a mail and it lands in the conversation (not tested for vendors). | Pending | Pending | Not built yet | Vendor | E-mail reply to request
Weather fallback by the nearest store | For cities the weather service cannot find, use the nearest store of the same cluster. | Pending | Pending | Not built yet | Manager/Admin | No direct equivalent
Calendar fix for reopened tickets | A reopened ticket counts as open for its whole life in the calendar; correct it from the history. | Pending | Pending | Not built yet | Manager/Admin | No direct equivalent
CK Desk Bot | A question-and-answer assistant on tickets and knowledge (plan only). | Pending | Pending | Not built yet | Requester, Technician | Zia
Google Workspace user sync | Create and update users from Google Workspace (plan only). | Pending | Pending | Not built yet | Manager/Admin | AD / LDAP import

## ManageEngine has more
ManageEngine ServiceDesk Plus area | What it gives | In CK Desk? | Notes (from general knowledge of the product - check against your edition)
Problem management | Find the root cause of repeated incidents and link them. | Not in CK Desk | Partial idea: "same issue again" lists repeats but there is no Problem record.
Change management | Plan, approve and track changes with roll-out and back-out plans. | Not in CK Desk
Release management | Group changes into releases. | Not in CK Desk
Asset management and CMDB | Inventory of all assets, discovery, relationships, lifecycle. | Partial | CK Desk has AC and Genset lists from Google Sheets, no discovery and no general assets.
Software licences and contracts | Track licences, contracts, warranty and expiry alerts. | Not in CK Desk | AMC vendor is only a text on the AC.
Purchase module | Purchase requests, orders and receipts for all items. | Partial | CK Desk has vendor quotes and POs for repairs only.
Self-service portal extras | Announcements, catalogue browsing, solutions suggested while typing. | Partial | Create Request page and Knowledge Base exist; no announcements or suggestions.
Mobile app | Native iOS and Android apps for technicians and requesters. | Not in CK Desk | The web app is responsive and has browser push.
AI assistant (Zia) and chatbot | Suggestions, auto-summaries, a chatbot. | Partial | "Catch me up" summary exists; Bot is a plan; AI classification is built but switched off.
Remote control | Take over a user's computer. | Not in CK Desk
Preventive maintenance / scheduled requests | Auto-create recurring tickets (for example monthly AC service). | Not in CK Desk | Worth considering for AC servicing.
Technician shifts and on-call | Availability, shifts, on-call schedules. | Not in CK Desk
Custom modules and orchestration | Build your own modules and automate across tools. | Not in CK Desk | Business Rules cover automation inside CK Desk only.
Integrations marketplace | Slack, Teams, Jira and many others. | Partial | CK Desk integrates with Google Sheets, the mailbox and a weather service.
Multi-level SLA escalation | Several escalation levels per SLA. | Partial | CK Desk has rule-based escalation and alerts.
Request merge and duplicate detection | Merge duplicate requests. | Partial | CK Desk blocks double submits; no merge screen.